## Sheet1
Milestone # | Description | Deliverables | Completion Date (if applicable) | Payment Amount
1 | Completion of kickoff meeting and planning session | Kickoff Meeting | 2024-11-01 | 1000
2 | Submission of QR 1, summarizing progress toward the Data Structure Report | Quarterly Report 1 (Oct-Dec) | 2024-12-01 | 1000
3 | 2-3 page report proposing the final data structure, including the information fields (columns), the data production process, and validation measures. | Data Structure Proposal | 2025-03-01 | 5000
5 | Submission of QR 2, summarizing the Data Structure Report and progress toward producing the final dataset | Quarterly Report 2 (Jan-Mar) | 2025-04-01 | 4000
6 | A final dataset for all pilot countries | Final Dataset | 2025-05-01 | 8020
7 | A draft of DevLab's contributions to the Final Report, including a summary of the data being produced, results of data validation analyses, and preliminary substantive findings. | Final Report Draft | 2025-06-01 | 10000
8 | Submission of QR 3, summarizing the final dataset and progress toward the final report. | Quarterly Report 4 (Apr-Jun) | 2025-07-01 | 2000
9 | A copy of DevLab's contributions to the Final Report, incorporating feedback from the draft Final Report. | Final Report Submission | 2025-08-01 | 8000
10 | Submission of QR 4, summarizing the final report. | Quarterly Report 1 (Jul-Sept) | 2025-10-01 | 1600
11 | Contributions to all dissemination activities in Y2 | Final Presentation | 2026-01-01 | 4380